Final Project Workplan

Position-Specific Career Lifecycle Curves in Professional Football

Prepared from the project instructions, proposal, and proposal presentation deck

Planning assumptions Code and presentation are the first priority, because presentation may happen before the written report. Technical execution is distributed across A, B, C, and D so every core contributor touches advanced Python work. E leads the presentation workflow and later owns final report integration and editing, even if ABCD write most of the technical content.

Table 1. Code + Presentation Workplan

每个人单独一个 notebook + 一个共享主 notebook （00_final_results_pipeline.ipynb）

+ 尽量把关键函数写进 .py

| Person | Primary ownership | Detailed responsibilities | Concrete outputs and checkpoints | Collaboration / handoff requirements |
| --- | --- | --- | --- | --- |
| A 4.16 | Data preprocessing + Early technical execution (01_data_preprocessing.ipynb) | 1. Build the shared baseline pipeline for data loading, cleaning, validation, and core table linkage. 2. Clean player_profiles, player_market_values, and player_performances, including .txt preprocessing, date parsing, column harmonization, dtype cleanup, and duplicate checks. 3. Create the analysis-ready merged backbone dataset and a short data dictionary for the whole team. 4. Run the first round of profiling on loading, cleaning, merging, and age construction. 5. Implement low-risk optimizations early: vectorized age calculation, better dtypes, categorical encoding, column pruning, and removal of obvious Python loops. | 01_A_preprocessing_and_merge.ipynb A 的主 notebook。负责读原始数据、清洗、统一列名、parse date、compute age、merge、输出 backbone dataset。 a_preprocessing_utils.py 把重复用的函数抽出来，比如 clean_profiles()、clean_market_values()、build_backbone_dataset() player_*_clean.parquet 三张清洗后的中间表 player_lifecycle_backbone.parquet 最重要，这是 B/C/D 后面统一使用的冻结版本 A_data_preprocessing_methods.md 给 report 里的 data/preprocessing/methods section 用 A_preprocessing_profile.md 记录 loading、cleaning、merging、age construction 的 bottleneck 和 early optimization data_dictionary.csv 给全组统一字段解释 | A must freeze the shared cleaned dataset before B, C, and D start final analysis. A should notify the team immediately if any schema mismatch, missing field, or date inconsistency affects all three research questions. |
| B 4.17- 4.18 | Research Question 1 Peak market value age analysis + RQ1-side technical execution (02_rq1_peak_age.ipynb) | 1. Define and implement the metric for peak market value age by position. 2. Decide sample filters needed for RQ1, but keep them aligned with team-wide data rules. 3. Produce the main RQ1 figures and statistical comparisons across broad position groups. 4. Profile the peak-age computation workflow and identify repeated sorts, groupby calls, or loops that can be improved. 5. Apply at least one concrete optimization to the RQ1 pipeline, such as vectorized extraction logic or reduced repeated grouping. | 02_B_rq1_peak_age_analysis.ipynb 从 A 的 player_lifecycle_backbone.parquet 读数据，计算 peak age，做 position-level comparison 和统计检验 b_rq1_peak_age_utils.py 放 peak age extraction、summary stats、plots 的函数 两张 figure 至少 1 到 2 张 presentation-ready 图B_rq1_peak_age_summary.csv 放按位置汇总的 mean/median/count 等 B_rq1_profile.md 说明 RQ1 哪一步慢，做了什么优化 B_rq1_peak_age_results.md report 里的 RQ1 subsection | B must use A's frozen cleaned data and common age / position definitions. B should coordinate with E on figure titles, labels, and the exact wording that appears on slides. |
| C 4.17- 4.18 | Research Question 2 Peak performance profile analysis + RQ2-side technical execution (03_rq2_peak_performance.ipynb) | 1. Define the performance metrics used for peak-performance comparisons across positions. 2. Build the grouped performance analysis workflow, including any time or age alignment needed for the chosen metrics. 3. Produce the main RQ2 visualizations and formal comparisons. 4. Profile grouped performance aggregation, smoothing, rolling logic, or repeated joins if they are part of the workflow. 5. Implement at least one optimization for RQ2, such as vectorized aggregation, reduced repeated joins, or better intermediate caching. | 按更合理的时间键去对齐market value backbone 和 cleaned performance table两组数据 由于minutes_played 缺失很多，做 performance analysis 时要谨慎定义指标，做进一步过滤和定义，不能默认这个变量对全样本都可靠 03_C_rq2_peak_performance_analysis.ipynb 定义 peak performance 指标，完成 age/time alignment，做比较和图表 c_rq2_performance_utils.py 放 grouped aggregation、alignment、metric construction 等函数 figure + summary table 给 slides 和 report 直接用 C_rq2_profile.md 记录 aggregation、rolling、joins 等 bottleneck 和优化 C_rq2_peak_performance_results.md report 里的 RQ2 subsection | C must keep the performance definition realistic and presentation-friendly. If RQ2 becomes too broad, C should narrow to the most interpretable performance metrics first so the project still has a clean story for presentation. |
| D 4.17- 4.19 | Research Question 3 Post-peak decline analysis + Late technical execution and final speedup (04_rq3_post_peak_decline.ipynb 05_technical_execution_optimization.ipynb) | 1. Define and implement the decline metric after peak, including slope estimation or another decline summary that can be justified clearly. 2. Produce the main RQ3 plots and position-level comparisons. 3. After the three question pipelines stabilize, run the final round of profiling across the full analysis workflow. 4. Lead deeper optimization on the most important bottlenecks, especially trajectory calculations, repeated grouped operations, and decline estimation. 5. Measure before-vs-after runtime improvements and summarize final speedup results for the deck. | 04_D_rq3_post_peak_decline_analysis.ipynb 负责定义 post-peak decline metric，计算 decline slope，比较不同 position 的 decline 差异，产出 RQ3 的图和表。05_D_full_pipeline_profiling_and_optimization.ipynb 用来做全流程 profiling 和最终优化。负责整合 A/B/C 的 profiling notes，找 full pipeline 的主要 bottleneck，做 before vs after benchmark，整理最终 speedup 结果。src/d_rq3_decline_utils.py 放 RQ3 相关函数，比如 decline metric、slope estimation、post-peak data extraction。src/d_optimization_utils.py 放 profiling、timing、benchmark、优化后函数这些工具代码。 figures + summary table RQ3 主图，展示不同位置 decline 的比较结果。补充图，展示 decline 指标的分布情况。RQ3 结果汇总表。outputs/tables/D_final_benchmark_table.csv 最终 runtime 对比表，展示优化前后时间和 speedup。outputs/profiling/D_full_pipeline_profile.md 记录 full pipeline profiling 结果、主要 bottleneck、优化思路和 benchmark 结论。report/D_rq3_and_advanced_python.md 写 final report 里 D 负责的部分，包括 RQ3 results 和 advanced Python / technical execution section。 | D should collect profiling notes from A, B, and C and convert them into one unified technical story. D is the final owner of the advanced Python narrative shown in the presentation. |
| E 4.20-4.22 | Slides, Presentation | 1. Convert ABCD's outputs into a tight 5-minute final presentation. 2. Build the final technical execution slide using D's integrated material and ensure it fits the overall narrative. | Before the final rehearsal, E should deliver: - full slide deck with polished titles and aligned terminology - speaker notes or a short speaking outline - final order of slides and timing per slide - a Q&A prep sheet with likely professor questions and short answers | Even though E is not the main analysis owner, E must flag story gaps immediately when slide logic and actual results do not match. |

Table 2. Report Workplan

Recommendation: ABCD write the substance, E owns integration, editing, formatting, and final narrative consistency.

| Person | Report section ownership | Detailed writing responsibilities | Required evidence to include | Review / submission expectations |
| --- | --- | --- | --- | --- |
| A | Data and preprocessing section Shared methods backbone Intro input | 1. Write the data source, file structure, preprocessing, field validation, merge strategy, and common sample construction. 2. Describe how age is computed and how the shared cleaned dataset is built. 3. Draft the technical part of the methods section that every research question depends on. 4. Provide 1 short paragraph of factual input for the introduction, especially dataset scale, realism, and scope control. 5. Co-check that all report results use the same frozen data version. | A's section should include: - exact data files used - merge and filtering decisions - preprocessing choices that materially affect the analysis - any limitation caused by schema mismatch or missing sub-position fields | A should do one final pass to verify that report text matches the actual code and data pipeline. A must also help confirm that every group member can run or inspect the final cleaned-data workflow before submission. |
| B | RQ1 results subsection Peak market value age findings | 1. Write the RQ1 methods and results subsection in final report style, not slide style. 2. Explain how peak market value age is defined and compared across positions. 3. Include the main RQ1 figure or table and interpret the result clearly. 4. Briefly note any robustness check or sensitivity decision if it materially changes interpretation. | B's subsection should include: - definition of the peak-age metric - figure or table with position-level comparison - short interpretation tied directly to the research question - one sentence on computational handling if an optimization changed the implementation meaningfully | B must keep terminology identical to the slide deck and to the shared methods section. B should avoid rewriting global preprocessing details that already belong in A's section. |
| C | RQ2 results subsection Peak performance findings | 1. Write the RQ2 methods and results subsection with a clear definition of the selected performance metrics. 2. Explain how peak performance is compared across positions and why the chosen metrics are appropriate. 3. Include the main RQ2 figure or table and interpret the core takeaway. 4. State any scope narrowing clearly if only the most interpretable metrics are used in the final report. | C's subsection should include: - precise metric definition for peak performance - one clean figure or table - concise interpretation that connects to football and to the overall lifecycle story - one sentence on limitations if metric availability differs by position | C should align the final subsection with the exact plots shown or referenced in the presentation. If RQ2 becomes too noisy, C should simplify rather than over-explain. |
| D | RQ3 results subsection + Advanced Python / technical execution section | 1. Write the RQ3 methods and results subsection, including the final definition of decline after peak. 2. Write the dedicated advanced Python section that explains profiling, bottlenecks, optimization choices, and benchmark results. 3. Summarize the distributed technical contributions from A, B, C, and D in one coherent section. 4. Include before-vs-after runtime evidence and explain which optimizations were actually retained in the final workflow. | D's contribution should include: - decline metric definition and main result figure or table - technical execution summary with profiling tools used - bottleneck explanation grounded in the actual pipeline - final speedup or runtime comparison evidence | D should make sure the advanced Python section is concrete and evidence-based, not just a list of tools. D must coordinate with E so the technical section fits the report page budget without losing credibility. |
| E | Full report integration, editing, formatting, and conclusion ownership | 1. Assemble ABCD's drafted sections into one coherent report. 2. Rewrite transitions, unify terminology, tighten repetition, and keep the document within the page limit. 3. Write or heavily edit the introduction opening and the final conclusion / limitations section so the report reads as one project rather than four stitched mini-reports. 4. Select final figures, captions, titles, and layout order. 5. Perform the last consistency pass on formatting, headings, references to figures, and overall narrative flow. | E should deliver: - final report master version - consistent title, section hierarchy, and figure captions - polished introduction and conclusion - final formatting ready for each member's individual submission | E must return an edited version to the full team for one last technical accuracy check before submission. All members should sign off on the final report, but E is the integration owner. |

Suggested operating rule for the team

Freeze the cleaned shared dataset before final RQ analysis begins. Require every ABCD owner to keep a short technical log showing what was slow, how it was measured, what changed, and what improved. Do one presentation rehearsal freeze before moving the team's main attention to the report. Before final submission, all five members should review the same master report and the same code package.